## Retail_AfterSales (hidden)
Retail
AfterSales
Both

## Projectype (hidden)
Database
Campaign
Pre-Sales
Continuous Improvement
BI (Reporting/Dashboard)
Analytics (HANA)
Interactive
Harmony
Microsites

## Oleary_Status
Client_Name | Project_Priority | Open_Status | Retail_AfterSales | Project_Name | Project_Comments | Project Type | Start_Date | Planned_End_Date | Actual_End_Date | Project_Description | Project_Status | Project_Constraints | Schedule | Budget | Client_Satisfaction | Scope | Resources | Other_Risk
Autonation | 1 | Project Completed | Retail | Vehicle Inventory Feed Data |  | Database | 2018-09-13 | 2018-10-03 | 2018-10-03 | Addition of Vehicle Inventory data into the AutoNation database to be applied to the Vehicle Disposal logic | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation | 2 | Project Completed | Retail | Will Buy Your Car Feed Data to the Database |  | Database | 2018-10-03 | 2018-10-30 | 2018-10-29 | Additionof the AutoNation Seller/Trade-In data (Buy Your Car Feed) to the AutoNation database | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation | 3 | Project In-Progress | Retail | CDK Integration |  | Database | 2018-10-20 | 2018-11-20 | 2018-11-20 | sSourcinging CDK data direct from CDK vs AN. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation | 4 | Project Completed | Retail | Divestiture Deletions |  | Database | 2018-10-23 | 2018-10-25 | 2018-10-25 | Deleting all AutoNation divested stores. This is a 40 hour process | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation | 5 | Project Completed | Retail | Recall Phone Opt Out Feed |  | Database | 2018-10-23 | 2018-10-31 | 2018-10-31 | Implementing a new Phone Opt Out feed from an AutoNation vendor | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation | 6 | Project Completed | Retail | Will Buy Your Car Feed Post Production Analysis | Delivered but not closed because the client is still reviewing the research provided | Database | 2018-10-30 | 2018-11-09 | 2018-11-09 | Client requested research for a completed project that wasn't included in the project LOE |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation | 7 | Project Completed | Retail | Service Appointment Source Integration |  | Database | 2018-10-30 | 2018-11-15 | 2018-11-15 | Integrating a Source column in the AutoNation Service Appointment tables | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Not Started | Retail | Email/Mobile Scorecard Collison Changes |  | Database | 2018-12-19 | 2019-01-18 | 2019-01-18 | Changes to incorporate Collision Center data in the AutoNation Email/Mobile Scorecard report | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project In-Progress | AfterSales | 32 After Sales Campaigns Daily Automated Campaigns (15-DM, 13-EM, & 4-SMS) | Ongoing | Campaign |  |  |  | Epsilon is executing 32 After Sales campaigns for AutoNation (15-DM, 13-EM, & 4-SMS) | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project In-Progress | Retail | 10 Retail Campaigns | Ongoing | Campaign |  |  |  | Epsilon is executing 10 Retail campaigns for AutoNation (3-DM, 6-EM, & 1-SMS) | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Not Started | Retail | Campaign Changes Due to a New Auction Rep Feed |  | Campaign |  |  |  | AutoNation would like Epsilon to make changes to all their Auction Campaigns to suppress Reps that have an Inactive or Blank value in the Rep Active Flag |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project In-Progress | Retail | AutoNation Sales Repurchasing Campaign Development | Campaign requirements due date was 12/17 but approval was received on 1/14 | Campaign | 2018-12-03 | 2019-02-22 |  | AutoNation is combining two large campaigns into one (Serial Mail & Equity) |  | None | 2-Major Concerns | 5-Healthy | 5-Healthy | 4-Early Warning | 2-Major Concerns | 5-Healthy
Autonation |  | Project Completed | Retail | Changes to Sales Grid Campaign |  | Campaign | 2018-11-02 | 2018-11-16 | 2018-11-16 | AutoNation has submitted changes to the Sales Grid Email campaign. These changes requre extensive documentation and workflow changes |  | None | 4-Early Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Completed | Retail | Promotion History Delete Request | Epsilon gets weekly requests to delete promotion history data from AutoNation campaign developers | Database | 2018-11-26 | 2018-11-30 | 2018-12-29 | Epsilon gets weekly requests to delete promotion history data from AutoNation campaign developers |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Completed | Retail | Disposal Research | Epsilon had to stretch the timeline for this request due to resource constraints | Database | 2018-11-01 | 2018-12-07 | 2018-12-04 | AutoNation has asked Epsilon to research a list of 5MM VINs to compare the disposal counts in the database to the counts provided by Polk (AutoNation vendor) |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Completed | Retail | VDP Remarkeing: Harmony Conversion Data to the CDM | Epsilon is incorporating a Harmony Conversion feed into the database to support an AutoNation Vehicle Details Page Remarketing campaign | Database | 2018-12-03 | 2018-12-21 | 2018-12-21 | Epsilon is incorporating a Harmony Conversion feed into the database to support an AutoNation Vehicle Details Page Remarketing campaign |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Completed | Retail | VDP Remarketing: Inventory Feed to the CDM | Epsilon is incorporating a Harmony Conversion feed into the database to support an AutoNation Vehicle Details Page Remarketing campaign | Database | 2018-12-11 | 2018-12-21 | 2019-12-21 | Epsilon is incorporating a Harmony Conversion feed into the database to support an AutoNation Vehicle Details Page Remarketing campaign |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Autonation |  | Project Completed | Retail | Provide AutoNation with Database Documentation | Database team provided all the requested documentation with the exception of updated data models | Database | 2019-01-22 | 2019-01-30 |  | AutoNation asked Epsilon to provide updated data models, max/min table size, database size, impact of conversion and pixel data on the database, and size of the inventory table |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | Nissan Small Car Campaign Data |  | Database | 2018-10-01 | 2018-10-31 | 2018-10-01 | Montly Product Email Data creation and transfer to Harmony | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | Nissan SUV Campaign Data |  | Database | 2018-10-01 | 2018-10-31 | 2018-10-01 | Montly Product Email Data creation and transfer to Harmony | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy | 5-Healthy
GM |  | Project Completed | Retail | GM - CSSR Data Integration Into the Database |  | Database | 2018-06-13 | 2018-10-19 | 2018-10-12 | Integrating the CSSR Customer, Vehicle, Sales, Service, and Communication data into the GM database |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project Completed | Retail | GM-IMR Dashboard Database Development and Load - Conversant Data |  | Database | 2018-09-24 | 2018-10-24 | 2018-10-19 | Database implementation to support the IMR Dashboard project - Conversant Impression and Conversion Data | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project Completed | Retail | GM-IMR Dashboard Database Development and Load - Search and Social Data |  | Database | 2018-09-24 | 2018-11-02 | 2018-11-02 | Database implementation to support the IMR Dashboard project - incorporating the Search, Social, and Analytics Data | On-Time | Scope Creep | 4-Early Warning | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy | 5-Healthy
GM |  | Project Completed | Retail | GM-IMR Dashboard Database Development and Load - Analytics Data |  | Database | 2018-09-24 | 2018-12-15 | 2018-11-30 | Database implementation to support the IMR Dashboard project | Late | Resources Needed | 2-Major Concerns | 5-Healthy | 3-Warning | 3-Warning | 3-Warning | 3-Warning
GM |  | Project Completed | Retail | IMR Dealer Enrollment Data Integration into the Database |  | Database | 2024-10-10 | 2018-12-15 | 2018-11-30 |  |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project Completed | Retail | GM-IMR Dashboard Database Development and Load - Data Load into HANA |  | Database | 2018-09-24 | 2018-12-01 | 2018-11-15 | Database implementation to support the IMR Dashboard project | Late | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project Completed | Retail | Submit a Risk Acceptance Document for the short term Single Sign On Solution for the CSSR Portal and the IMR Dashboard |  | Interactive | 2018-11-08 | 2018-11-30 | 2018-11-26 | The Single Sign On (SSO) token solution that the Portal Team outlined is currently in production for other clients as an internal SSO, but now the SSO we plan to implement will be internal to external, so we want to be sure the approach checks out from a security standpoint. |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project In-Progress | Retail | GM Adhoc CSSR Data Integration into the Database |  | Database | 2018-11-15 | 2019-01-18 |  |  |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project Not Started | Retail | GM CSSR Action History Integration into the Database |  | Database | [5 empty] | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM |  | Project Not Started | Retail | GM Adhoc Files for Conversant Integration into the Database |  | Database | [5 empty] | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | Nissan Murano LPA Campaign Data |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-02 | Adhoc Product Emal Data creation and transfer to Harmony | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 10 | Project In-Progress | Retail | Nissan - Owner Profile Phase 2 |  | BI (Reporting/Dashboard) | 2018-11-01 | 2019-03-01 |  | Owner Profile Phase 2 | On-Time | None | 5-Healthy | 3-Warning | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 9 | Project In-Progress | Retail | Nissan - Email Metrics Report |  | BI (Reporting/Dashboard) | 2018-08-30 | 2019-02-28 |  | Email Metrics Report | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 3 | Project Deployed | Retail | Nissan - Handraiser/Lead Tab to Executive Summary Report |  | BI (Reporting/Dashboard) | 2018-04-10 | 2018-06-30 | 2018-06-14 | Handraiser/Lead Tab to Executive Summary Report | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 5 | Project Deployed | Retail | Nissan - Projected vs. Actual Incremental Sales |  | BI (Reporting/Dashboard) | 2018-08-30 | 2018-10-26 | 2018-10-24 | Projected vs. Actual Incremental Sales | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 4 | Project Deployed | Retail | Nissan - Projected vs. Actual Incremental Sales (Table Build) |  | BI (Reporting/Dashboard) | 2018-10-31 | 2018-12-31 | 2018-11-15 | Projected vs. Actual Incremental Sales (Table Build) | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 2 | Project Deployed | Retail | Nissan - Owner Profile Phase 1 |  | BI (Reporting/Dashboard) | 2018-01-15 | 2018-04-30 | 2018-04-15 | Owner Profile Phase 1 | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 1 | Project Deployed | Retail | Nissan - Campaign-level Incremental Sales |  | BI (Reporting/Dashboard) | 2018-02-01 | 2018-03-31 | 2018-03-15 | Campaign-level Incremental Sales | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 6 | Project Deployed | Retail | Nissan - Topline Incremental Sales |  | BI (Reporting/Dashboard) | 2018-08-30 | 2018-12-01 | 2018-11-01 | Topline Incremental Sales | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy
Business Intelligence | 11 | Project In-Progress | Retail | Nissan - Topline Overal Cost Change to Executive Summary |  | BI (Reporting/Dashboard) | 2018-10-05 | 2019-03-01 |  | NIS - Topline Overal Cost Change to Executive Summary | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 11 | Project In-Progress | Retail | Infiniti - Topline Overal Cost Change to Executive Summary |  | BI (Reporting/Dashboard) | 2018-10-05 | 2019-03-01 |  | INF - Topline Overal Cost Change to Executive Summary | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 7 | Project Deployed | Retail | Nissan - Non-Model Specific Owner Profile Report |  | BI (Reporting/Dashboard) | 2018-10-22 | 2018-11-16 | 2018-11-06 | Nissan - Non-Model Specific Owner Profile Report | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 8 | Project Delivered | Retail | Infiniti - Non-Model Specific Owner Profile Report |  | BI (Reporting/Dashboard) | 2018-11-01 | 2018-11-16 | 2018-11-07 | Infiniti - Non-Model Specific Owner Profile Report | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project Completed | Retail | BMWFS - Phase 1 Tableau ROMI Report revisions |  | BI (Reporting/Dashboard) | 2018-07-01 | 2018-09-30 | 2018-09-30 | Phase 1 Tableau Dashboards delivered. Working with agency Partners & Napiers to design some new UX layouts for phase 2. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project Completed | Retail | BMWFS - Hana Tables |  | Analytics (HANA) | 2018-07-01 | 2019-01-01 | 2018-09-30 | BMWFS - Hana Tables | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project Completed | Retail | BMWNA - 2018 Report Maintenance |  | BI (Reporting/Dashboard) | 2018-01-01 | 2018-12-31 | 2018-12-31 | BMWNA - 2018 Report Maintenance |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 5 | Project In-Progress | Retail | BMWNA - 2019 Report Maintenance |  | BI (Reporting/Dashboard) | 2019-01-01 | 2019-12-31 |  | BMWNA - 2019 Report Maintenance | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 4 | Project In-Progress | Retail | BMWFS - Blue Ocean Strategy |  | BI (Reporting/Dashboard) | 2018-07-01 | 2019-03-30 |  | BMWFS - Blue Ocean Strategy | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project Completed | Retail | BMWFS - Loyalty Rates - Non-FS Research |  | BI (Reporting/Dashboard) | 2018-08-16 | 2018-11-30 | 2018-11-27 | BMWFS - Loyalty Rates Research | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project Completed | Retail | BMWFS - Loyalty Stream Report Performance Enhancement |  | BI (Reporting/Dashboard) | 2018-07-25 | 2018-08-31 | 2018-08-13 | BMWFS - Loyalty Stream Report Performance Enhancement | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 3 | Project In-Progress | Retail | BMW New Server Maintenance |  | BI (Reporting/Dashboard) | 2019-01-15 | 2019-03-01 |  | BMW New Server Maintenance | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project Completed | Retail | BMW Server Migration |  | BI (Reporting/Dashboard) | 2018-12-07 | 2019-01-11 | 2019-01-11 | BMW Server Migration | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 2 | Project On-Hold | Retail | BMWFS - New Conversion type conquest |  | BI (Reporting/Dashboard) | 2019-01-22 | 2019-03-01 |  | BMWFS -New Conversion type conquest | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 7 | Project On-Hold | Retail | BMWFS - Conquest Response Data - Acquireweb |  | BI (Reporting/Dashboard) | 2018-03-01 | 2019-03-30 |  | BMWFS - Conquest Response Data - Acquireweb | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 6 | Project On-Hold | Retail | BMWFS - Develop Fast Reporting Deck |  | BI (Reporting/Dashboard) | 2018-10-23 | 2018-12-31 |  | BMWFS - Develop Fast Reporting Deck | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM - Dealer Digital Dashboard with Jason Wiley |  | BI (Reporting/Dashboard) | 2018-08-01 | 2018-12-01 |  | GM - Dealer Digital Dashboard with Jason Wiley | On-Time | Resources Needed | 4-Early Warning | 5-Healthy | 4-Early Warning | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM - Dealer Digital Dashboard BI Portal Setup |  | BI (Reporting/Dashboard) | 2018-08-01 | 2018-12-01 |  | Setup BI portal for GM dealers for IMR Enhanced Digital Advertising | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM - Dealer Digital Dashboard Test Data Setup |  | BI (Reporting/Dashboard) | 2018-08-01 | 2018-12-01 |  | Building test data for GM IMR dashboard. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM CSSR 3.0 Analytics Dashboard Reporting with Frank Popyk |  | BI (Reporting/Dashboard) | 2018-12-01 | 2019-02-15 |  | GM CSSR 3.0 Analytics Dashboard Reporting with Frank Popyk | On-Time | Resources Needed | 4-Early Warning | 5-Healthy | 4-Early Warning | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM CSSR 3.0 Analytics Reporting with Frank Popyk |  | BI (Reporting/Dashboard) | 2019-01-02 | 2019-03-31 |  | GM CSSR 3.0 Analytics Reporting with Frank Popyk | Not Started | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM CSSR 3.0 Analytics Data Lake in HANA |  | Analytics (HANA) | 2018-12-01 | 2019-02-15 |  | GM CSSR 3.0 Analytics Data Lake in HANA | On-Time | Resources Needed | 4-Early Warning | 5-Healthy | 4-Early Warning | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project Completed | Retail | GM CSSR 3 GM: Data Output BO reports development |  | BI (Reporting/Dashboard) | 2018-12-11 | 2019-01-01 | 2019-01-01 | GM CSSR 3 GM: Data Output BO reports |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 1 | Project On-Hold | Retail | GM CSSR 3 GM: Data Output BO reports UAT/schedule |  | BI (Reporting/Dashboard) | 2019-01-01 | 2019-03-01 |  | GM CSSR 3 GM: Data Output BO reports | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence | 1 | Project In-Progress | Retail | BMWFS - Phase 2 ROMI Tableau development |  | BI (Reporting/Dashboard) | 2018-12-01 | 2019-12-31 |  | BMWFS - Phase 2 ROMI Tableau development | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence | 1 | Project In-Progress | Retail | BMWFS - Phase 2 ROMI HANA development |  | Analytics (HANA) | 2018-12-01 | 2019-12-31 |  | BMWFS - Phase 2 ROMI HANA development | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | Ford 2 Dashboards - Scoped by Aaron Gerrick |  | Pre-Sales | 2019-01-01 | 2019-03-01 |  | Ford 2 Dashboards - Scoped by Aaron Gerrick | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | Ford Dealer Reporting - Scoped by Aaron Gerrick |  | Pre-Sales | 2019-01-01 | 2019-03-01 |  | Ford Dealer Reporting - Scoped by Aaron Gerrick | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | Ford Reporting - HANA development |  | Pre-Sales | 2019-01-01 | 2019-03-01 |  | Ford Reporting - HANA development | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | Nissan - Nissan Commercial Executive Summary Report and Dashboard |  | BI (Reporting/Dashboard) | 2018-11-12 | 2019-03-30 |  | Nissan - Nissan Commercial Executive Summary Report and Dashboard | Not Started | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 4-Early Warning
Business Intelligence |  | Project In-Progress | Retail | Nissan - Sales Match Dashboard |  | BI (Reporting/Dashboard) | 2018-08-30 | 2019-03-30 |  | Nissan - Sales Match Dashboard | On-Hold | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning
Business Intelligence |  | Project In-Progress | Retail | Nissan - Switch Household Logic in Reports |  | BI (Reporting/Dashboard) | 2018-08-30 | 2019-03-30 |  | Nissan - Switch Household Logic in Reports | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning
GM Financial |  | Project Completed | Retail | Campaign Support Run Contract |  | Campaign | 2018-10-01 | 2018-11-09 | 2018-11-14 | Campaign Support | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy
GM Financial |  | Project Delivered | Retail | OCA SFDC Integration Campaign |  | Campaign | 2018-09-24 | 2018-10-19 | 2018-10-23 | SFDC Integration to Campaign with OCA Campaign built off the import and export criteria back to SFDC | Delivered | None | 4-Early Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM Financial |  | Project In-Progress | Retail | OCA Campaign Update |  | Campaign | 2019-01-01 | 2019-01-31 |  | Campaign creative update and approval | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM Financial |  | Project Completed | Retail | Legacy Data Migration |  | Campaign | 2018-10-01 | 2018-10-19 | 2018-10-19 | Migrate Legacy Data from Campaign 6.1 to 7.0 | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM Financial |  | Project Completed | Retail | Experience Cloud Integration |  | Continuous Improvement | 2018-11-01 | 2019-01-01 | 2019-01-01 | Adobe Platform Integration and Enhancements. Will expand into multiple project once contracts are fully completed and agreed upon. | On-Time | Client Commitment | 4-Early Warning | 4-Early Warning | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
GM Financial |  | Project Deployed | Retail | Preference Center Migration |  | Campaign | 2018-11-14 | 2018-11-30 | 2018-12-06 | Complete unauth and authenticated preference cener inegration. Removal of Epsilon Hosted. | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM Financial |  | Project Deployed | Retail | Unsubscribe Migration |  | Campaign | 2018-11-14 | 2018-11-30 | 2018-12-03 | Removal of Epsilon Hosted. | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM Financial |  | Project In-Progress | Retail | SMS implementation |  | Campaign | 2018-11-14 | 2018-12-31 |  | Implement 3C gateway for Campaign SMS distribution | On-Time | STS Delays (Hardware/Software) | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
GM Financial |  | Project Completed | Retail | Adobe Campaign and Analytics Sync |  | Campaign | 2018-10-23 | 2019-01-01 | 2019-01-07 | Integration with Adobe Analytics, Met with Analytics team to discuss base level naming conventions, roadmmap, and enhancements. First phase will complete synchronization of naming conventions cross platform. | On-Time | Client Commitment | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
GM Financial |  | Project Late | Retail | DataHub Architectual Design |  | Campaign | 2018-11-12 | 2018-12-31 |  | Collaborate with the other experience cloud products to decipher what data is needed and orchestrate a unified DataHub | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 3-Warning | 5-Healthy
GM Financial |  | Project Not Started | Retail | DataHub Contruction |  | Campaign | 2019-01-01 | 2019-01-31 |  | Begin work on DataHub reconstruction | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 3-Warning | 5-Healthy
GM Financial |  | Project Completed | Retail | Campaign Instance Mirror |  | Campaign | 2018-11-12 | 2018-12-01 | 2018-12-01 | Mirror instances on all levels. Cleanup datamart to reflect the current architecture of GMF with the additional enhancements and special project requests | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 3-Warning | 5-Healthy
AT&T |  | Project Completed | Retail | Recharge Promotion for October Halloween |  | Microsites | 2018-10-22 | 2018-10-29 | 2019-10-24 | Update October end recharge promotion banner in AT&T Prepaid microsite | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Completed | Retail | Recharge Promotion for Thanksgiving |  | Microsites | 2018-11-12 | 2018-11-19 | 2018-11-19 | Update Mid November recharge promotion banner in AT&T Prepaid microsite | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Completed | Retail | Recharge Promotion for Cyber Monday |  | Microsites | 2018-11-21 | 2018-11-29 | 2018-11-29 | Update Thanksgiving recharge promotion banner in AT&T Prepaid microsite | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Completed | Retail | Recharge Promotion for December |  | Microsites | 2018-12-10 | 2018-12-17 | 2018-12-17 | Update December month recharge promotion banner in AT&T Prepaid microsite | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Completed | Retail | Recharge Promotion for New Year |  | Microsites | 2018-12-21 | 2019-01-09 | 2019-01-08 | Update New Year's recharge promotion banner in AT&T Prepaid microsite |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Completed | Retail | FAQ Updates in Prepaid site |  | Microsites | 2019-01-04 | 2019-01-18 | 2019-01-14 | Add new question and answer to FAQ list on the AT&T prepaid microsite |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project In-Progress | Retail | Recharge Promotion for Winter/Super Bowl |  | Microsites | 2019-01-17 | 2019-01-31 |  | Update Winter/Super Bowl recharge promotion banner in AT&T Prepaid microsite | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Valentine's Day |  | Microsites | 2019-02-07 | 2019-02-20 |  | Update Valentine's Day recharge promotion banner in AT&T Prepaid microsite | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Mardi Gras |  | Microsites | 2019-02-21 | 2019-03-06 |  | Update Mardi Gras recharge promotion banner in AT&T Prepaid microsite | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for St.Patrick's Day |  | Microsites | 2019-03-07 | 2019-03-20 |  | Update St.Patrick's Day recharge promotion banner in AT&T Prepaid microsite | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for April Fool's Day |  | Microsites | 2019-03-21 | 2019-04-03 |  | Update April Fool's Day recharge promotion banner in AT&T Prepaid microsite | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Sprint 2019 |  | Microsites | 2019-04-11 | 2019-04-24 |  | Update Spring 2019 recharge promotion banner in AT&T Prepaid microsite | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Mother's Day |  | Microsites | 2019-05-02 | 2019-05-15 |  | Update Mother's Day recharge promotion banner in AT&T Prepaid microsite | 5-Healthy | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Memorial Day |  | Microsites | 2019-05-16 | 2019-05-29 |  | Update Memorial Day 2019 recharge promotion banner in AT&T Prepaid microsite | 5-Healthy | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Father's Day |  | Microsites | 2019-06-06 | 2019-06-19 |  | Update Father's Day recharge promotion banner in AT&T Prepaid microsite | 5-Healthy | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Not Started | Retail | Recharge Promotion for Independence Day |  | Microsites | 2019-06-24 | 2019-07-10 |  | Update Independence Day recharge promotion banner in AT&T Prepaid microsite | 5-Healthy | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
AT&T |  | Project Completed | Retail | Recharge Tier for CT 15814 |  | Interactive | 2018-10-24 | 2018-11-09 | 2018-11-09 | Update Code to fix the issues with rounding of the Tiers for Care Type 15814 | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Completed | Retail | MINI Offline Events upload to Facebook |  | Database , Interactive | 2018-07-06 | 2018-10-30 | 2018-10-30 | BMWNA- Upload MINI offline events to Facebook | Delivered | Scope Creep | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Completed | Retail | Digital Integration - Live Ramp onboard |  | Database | 2018-08-15 | 2018-10-30 | 2018-10-30 | Onboard Live ramp as a third party vendor for BMW and share the customer file with Live ramp. Currently this file is being shared with Experian. | Delivered | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Completed | Retail | Digital Integration - Hashed email in Retail file to Universal Machan |  | Database | 2018-08-15 | 2018-10-30 | 2018-11-08 | This project is to encrypt email address with SHA256 algorithm in the retail file being sent to UM | Late | None | 4-Early Warning | 5-Healthy | 4-Early Warning | 3-Warning | 1-Concerns Realized | 5-Healthy
BMWNA |  | Project Completed | Retail | New UNICA Server Migrtion |  | Campaign | 2018-06-01 | 2018-11-30 | 2018-11-15 | It is to migrate Campaigns from the current UNICA server to the new UNICA server | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | UNICA upgrade to U10 |  | Campaign | 2018-12-01 | 2019-02-15 |  | Upgrade UNICA version to U10 in UAT and PROD |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Late | Retail | Cust intel data issue - one profile with 125 VINs |  | Database | 2018-09-01 | 2018-11-15 |  | BMW provided details on an issue where one profile maps to 125 VINs. | Late | Resources Needed | 3-Warning | 5-Healthy | 4-Early Warning | 5-Healthy | 1-Concerns Realized | 5-Healthy
BMWNA |  | Project Completed | Retail | Episilon Recall Interface file |  | Database | 2018-11-01 | 2018-12-12 | 2018-12-12 | It appears that the format of the recall file is changing. Full VIN instead of chassis_number. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Completed | Retail | Amend Fact Promotion History - improvements |  | Database | 2018-10-31 | 2018-11-30 | 2018-11-29 | There are two issues with this table from DBA. One is the size of the table and another is the number of columns: o Look into moving most of not all of the attribute columns to a child table o Check with client to see how far back promotion history is needed for campaigns | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | Tables getting created in UNICA - Over 60K+ tables and probable issues as IBM recommends only 40K+ tables |  | Database | 2018-10-01 | 2019-02-28 |  | Netezza DBA recommends to archive these tables: Check with Raare team to see if we can archive anything older than 3 months. Test performance running extract/gzip from ETL server using nzzql | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Delivered | Retail | MyBMW -Preferred Sales/Service |  | Interactive | 2018-09-01 | 2019-03-31 |  | This project is related to the new Website MyBMW going live | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | MyBMW - External Preference Center |  | Interactive | 2018-09-01 | 2019-03-31 |  | This project is related to the new Website MyBMW going live | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
BMWNA |  | Project Deployed | Retail | MINI USA web Registration |  | Database , Interactive | 2018-10-16 | 2018-12-15 | 2018-12-07 | MyBMW website to do samething as in MINI. 1. All of the MyBMW project work is - introducing a new profile type, MyBMW and MyMINI registrants. Via syncparty with a new role. 2. LOE to add a new profile type that we receive through the Sync Party - to accept a different value MINI | On-Time | Client Commitment | 3-Warning | 3-Warning | 5-Healthy | 5-Healthy | 3-Warning | 1-Concerns Realized
BMWNA |  | Project In-Progress | Retail | NCOA changes to reduce the agility transactions |  | Database | 2018-11-01 | 2018-12-27 |  | This is to create a process to reduce agility transactions from NCOA file | Not Started | Client Commitment | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Completed | Retail | Amend Fact Promotion History |  | Database | 2018-09-15 | 2018-10-24 | 2018-10-17 | This is to amend FACT PROMOTION HISTORY table with addition 90 columns value pairs attributes | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | Prospect Promo Conversions |  | Database | 2018-11-01 | 2018-12-27 |  | The BMW event teams have requested that we record subsequent retail conversions. | Not Started | Client Commitment | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | Cust Intel - Prospect Survey updates |  | Database | 2018-11-01 | 2018-12-27 |  | Update Customer Intel Prospect Survey responses to support Medallia and Qualtrics | Not Started | Client Commitment | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project Not Started | Retail | VIN17 Updates |  | Database | 2019-02-01 | 2019-03-31 |  | Update database code to accept Chasis as an unique number. |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | Consumer Data Enhancement using TSP |  | Database | 2018-01-02 | 2019-03-31 |  | This project is requested by BMWNA to replace Experian with TSP for providing services for consumer data enhancement. | Not Started | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project On-Hold | Retail | Conversant CRM and Modeled Acquisition |  | Database | 2018-01-02 | 2019-03-31 |  | This is to coordinate with Conversant team for CRM and Model acquisition project for BMWNA. | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWNA |  | Project In-Progress | Retail | New ETL Server Migration |  | Database | 2018-10-01 | 2019-02-28 |  | This is to migrate from old ETL Server to new ETL server |  | Resources Needed | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
BMWFS |  | Project Completed | Retail | Centralized Suppression Process |  | Campaign, Database | 2018-07-25 | 2018-10-31 | 2018-11-30 | Create a centeralized suppression process for all the campaigns | Late | Scope Creep | 2-Major Concerns | 3-Warning | 2-Major Concerns | 1-Concerns Realized | 1-Concerns Realized | 1-Concerns Realized
BMWFS |  | Project Completed | Retail | Preference Center Search Criteria Updates |  | Interactive, Database | 2018-10-01 | 2018-11-30 | 2018-11-15 | Update Internal preference center to search using Customer Address | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project On-Hold | Retail | Automation of FAST OUTPUT |  | Database , Campaign, BI (Reporting/Dashboard), Harmony | 2018-10-25 | 2018-12-30 |  | This is to automate the FAST Committee Report Output | Not Started | Client Commitment | 5-Healthy | 2-Major Concerns | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
BMWFS |  | Project Completed | Retail | Update FS Customer and FS Customer Address processes to reduce agility transactions |  | Database , Interactive | 2018-10-25 | 2018-12-30 | 2018-12-27 | This is to fill in the gaps between Customer Address and Customer files to reduce the agility transactions | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
BMWFS |  | Project Late | Retail | Bad Dealer/Dealer ID update |  | Database | 2018-10-05 | 2018-11-09 |  | Change the business rules for FS_DD_LINK as few of the dealers did not update their financial account for their dealer id. | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
BMWFS |  | Project Completed | Retail | FS Customer Role - ETL Flag update |  | Campaign, Database | 2018-10-30 | 2018-12-15 | 2018-12-07 | Epsilon proposed to create MyAccount Indicator in DIM PROFILE CONTACT instead of MyBMW as MyBMW is going to be used for NA. Will update the Microsite rule to look for the profile id. | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
BMWFS |  | Project Completed | Retail | FS Customer Role - Back Pop file update (Historical file) |  | Database | 2018-10-26 | 2018-10-30 | 2018-10-30 | FSIT sent out the backpop file and it has been processed successfully. | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | BMWFS - METADATA REVIEW - MYFS CAMPAIGNS |  | Database , Campaign, BI (Reporting/Dashboard), Harmony | 2018-10-15 | 2019-03-31 |  | Review the MYFS campaigns and see what the best strategy is for changing the segmentation both historically and moving forward | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project Not Started | Retail | BMWFS - METADATA HISTORICAL UPDATE - X3 CONQUEST |  | Database , Campaign, BI (Reporting/Dashboard), Harmony | 2018-10-15 | 2019-03-31 |  | For the X3 Conquest Campaign, BMW would like to update the metadata and break the program into 2 separate campaigns: | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | BMWFS - QBR ITEM - Create 4th program_type category for conversions: Conquest |  | Database , Campaign, BI (Reporting/Dashboard), Harmony | 2018-10-15 | 2019-03-31 |  | Create a fourth program_type in the conversion table to account for CONQUEST. Right now all conquests are logged as LOYALTY | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project Not Started | Retail | BMWFS- SF Voice Data Migration |  | Database | 2019-01-31 | 2019-04-30 |  | Accept new SF voice survey files from BMWFS and process them in MDB |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project Not Started | Retail | MYFS CTA UPDATES - MINI |  | Database , Campaign, BI (Reporting/Dashboard), Harmony | 2018-10-15 | 2019-03-31 |  | Effort for CTA test for MyFS campaigns. | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project Not Started | Retail | FACT VEHICLE TRANSACTION History logic updates |  | Database , Campaign, BI (Reporting/Dashboard), Harmony | 2018-12-27 | 2019-03-31 |  | This is to enhance the logic to adhere to the new requirements for Fact vehicle transaction report. |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | BMWFS - Phase 2 Tableau ROMI Report revisions |  | Database | 2018-11-01 | 2019-03-31 |  | ROMI Phase 2, Provide Enhanced Data feeds to Analytics team | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project Not Started | Retail | Selligent Emails - replacement by Harmony |  | Database | 2018-01-02 | 2019-03-31 |  | BMWFS Requested to takeover Seligent scope by Harmony. Database to provide support related automation. | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | Monthly campaign support for 22 campaigns |  | Campaign | 2018-10-17 | 2018-12-31 |  | There are 22 monthly recurring campaigns that are being worked out to be delivered. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | Weekly campaign support for 18 campaigns |  | Campaign | 2018-10-17 | 2018-12-31 |  | There are 18 weekly recurring campaigns that are being worked out to be delivered. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | Daily campaign support for 9 campaigns |  | Campaign | 2018-10-17 | 2018-12-31 |  | There are 9 daily recurring campaigns that are being worked out to be delivered. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | Quarterly campaign support for 3 campaigns |  | Campaign | 2018-10-17 | 2018-12-31 |  | There are 3 quarterly recurring campaigns that are being worked out to be delivered. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
BMWFS |  | Project In-Progress | Retail | New BO Server Migration |  | BI (Reporting/Dashboard) | 2018-10-01 | 2019-01-31 |  | This is to migrate from old BO server to New BO Server |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Ford |  | Project In-Progress | Retail | FACET Q1 Sales Communications |  | Campaign | 2018-12-15 | 2019-03-31 |  | Deliver 12 DM, 19 EM and 5 Phone sales campaigns in Q1 2019 | None | None | 3-Warning | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Ford |  | Project In-Progress | AfterSales | FACET Q1 Service Communications |  | Campaign | 2018-12-15 | 2019-03-31 |  | Deliver 19 DM, 26 EM 9 Phone and 18 SMS service campaigns in Q1 2019 | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Ford |  | Project In-Progress | Retail | Hardware Refresh | Hardware ordered - ETA 2/1. Prioritized in STS queue. | Continuous Improvement | 2018-10-08 | 2019-05-31 |  | Reduce daily production issues and manual handholding required due to space and performance restrictions of current solution. This is required to maintain and support the business. | Management Commitment | STS Delays (Hardware/Software) | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project In-Progress | Retail | Billing Postage Increase |  | Database | 2019-01-21 | 2019-02-15 |  | Update billing code to account for postage price increase. This is required for February billing. |  | Resources Needed | 3-Warning | 5-Healthy | 3-Warning | 5-Healthy | 1-Concerns Realized | 5-Healthy
Ford |  | Project On-Hold | Retail | Storing Campaign Suppressions for Engagement Feed | On hold due to resource constraints | Database | 2019-01-28 | 2019-03-29 |  | Store campaign suppression codes to pass through to Ford in the Engagement Feed | Resources Needed | Resources Needed | 2-Major Concerns | 5-Healthy | 3-Warning | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Not Started | Retail | Defector coupon matrix logic changes and documentation | On hold due to resource constraints | Database | 2019-01-28 | 2019-03-29 |  | Document beginning to end data dependencies, load process and QC steps required for the quarterly defector campaign. Work with Account team on requirements and sign-off. The goal is to eliminate confusion and recurring issues. |  | Resources Needed | 2-Major Concerns | 5-Healthy | 3-Warning | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project On-Hold | Retail | Marchex | Project scoped - Pending Prioritization/Client Approval | Database |  |  |  | New project scoped - Pending Prioritization |  | Resources Needed | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Ford |  | Project On-Hold | Retail | Campaign Channel Report Automation | On hold due to resource constraints | Continuous Improvement | 2018-09-07 | 2018-11-30 |  | Automate the creation and distribution of the CCR report for each campaign | Resources Needed | Resources Needed | 1-Concerns Realized | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Ford |  | Project On-Hold | Retail | Automate FRMS QC Checks against production mail files | All EM completed and in production, DM - 5 campaigns in prod (PMA, Bday, ESPAP and ESPRN); remaining DM and Phone on hold | Continuous Improvement | 2018-08-01 | 2018-12-31 |  | Leverage FRMS to automate basic QC checks against the production DM and EM mail files. | Resources Needed | Resources Needed | 2-Major Concerns | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Ford |  | Project On-Hold | Retail | Processing multiple GDG batches (Ford daily batches) in one DB load. | On hold due to resource constraints | Continuous Improvement | 2018-11-13 | 2018-01-31 |  | Enhancing daily load process to enable processing multiple batches in one load. This will help in situations where Ford sends large volumes or catch-up files. Currently it can take days or even weeks to get caught up. This would streamline that catch-up process. | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 1-Concerns Realized | 5-Healthy
Ford |  | Project Completed | Retail | In Market Regional Offer Data - Trim Formatting Change |  | Database | 2018-01-15 | 2019-01-18 | 2019-01-18 | Change requested to remove "-" character from trim level. Manually corrected for January files. To avoid manual formatting adjustments requested for the vehicle trim after files are produced, a new process will be added to receive requirements from account team and construct the vehicle images ahead of time and send to account team for review/sign-off. All instructions will be provided from the account team via a confluence page. |  | Resources Needed | 3-Warning | 5-Healthy | 3-Warning | 5-Healthy | 3-Warning | 5-Healthy
Ford |  | Project Completed | Retail | January Regional Offer Process for InMarket |  | Database | 2019-01-02 | 2019-01-11 | 2019-01-11 | Once approved by client, Import/load monthly InMarket offers, append to files and QC |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | AfterSales | Quarterly process to load and create Defector Coupon Matrix | Coupon Issues discovered in UAT files - fix applied | Database | 2018-12-10 | 2018-12-18 | 2019-01-11 | Quarterly process to load and create Defector Coupon Matrix |  | None | 1-Concerns Realized | 5-Healthy | 3-Warning | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | AfterSales | PCG Quarterly Selection Process |  | Database | 2018-11-21 | 2018-12-31 | 2018-12-31 | Quarterly program control group selection process | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Ford |  | Project Completed | AfterSales | Q4 Holiday Campaigns |  | Campaign | 2018-10-01 | 2018-12-31 | 2018-12-31 | Q4 Holiday Campaigns - Development and Testing in October; Weely production execution in November - December | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Ford |  | Project Completed | AfterSales | Q1 Defector - enhance logic to pull in the Works defector coupons. |  | Database | 2018-12-04 | 2019-12-28 | 2018-12-28 | Defector - If coupon data is not available in portal B, pull in values from the metrics file | None | None | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | AfterSales | Defector Logic Changes - no SRO |  | Campaign | 2018-12-03 | 2018-12-31 | 2018-12-28 | Logic changes to increase Q1 Defector volume due to discontinuing SRO program. |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Ford |  | Project Completed | AfterSales | Program Control Group Changes for Q1 |  | Database | 2018-12-10 | 2018-12-31 | 2019-12-31 | Changing from VIN to HH level - Append force treated HH's to the Control Group extract to Cadence team |  | Resources Needed | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | AfterSales | PMA and Birthday - Changes to Default Coupons |  | Database | 2018-12-17 | 2018-12-31 | 2019-12-31 | PMA and Birthday - Changes to Default Coupons; tables/views are not changing…underlying coupon data is changing |  | Resources Needed | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | Retail | Regional Offer process training and transition to FACET |  | Campaign | 2018-11-05 | 2018-12-31 | 2018-12-31 | Regional Offer process training and transition to FACET - FACET is taking over process in Q1 | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | Retail | FACET Q4 Sales Communications |  | Campaign | 2018-09-15 | 2018-12-31 | 2018-12-31 | Deliver 3 recurring monthly, 4 quarterly, and 4-6 adhoc PO sales campaigns across DM, EM, Phone and SMS channels in Q4 | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Ford |  | Project Completed | AfterSales | FACET Q4 Service Communications |  | Campaign | 2018-09-15 | 2018-12-31 | 2018-12-31 | Deliver 1 recurring weekly, 4 recurring monthly, 2 quarterly and ~4-6 adhoc PO service campaigns across DM, EM, Phone and SMS channels in Q4 | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Ford |  | Project Completed | Retail | Non Ford Credit KBB - Q1 Changes |  | Campaign | 2018-12-03 | 2018-12-14 | 2018-12-14 | Business rules and logic changes on the extract to KBB to limit to targeted VINs. Underlying DB table changes required. | None | None | 3-Warning | 5-Healthy | 3-Warning | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | Retail | Automate DM and EM release to engagement | In progress but delayed due to resource constraints. Currently targeting 12/10 | Continuous Improvement | 2018-10-05 | 2018-11-02 | 2018-12-10 | Automate process to release campaigns to engagement feed | Resources Needed | Resources Needed | 1-Concerns Realized | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | AfterSales | Defector - Client UAT Changes |  | Campaign | 2018-10-22 | 2018-12-07 | 2018-12-07 | Changing the process and method of creating the client UAT test files and reports to enable the team to create the deliverables eariler and shave time from the overall schedule. | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Ford |  | Project Completed | AfterSales | PCG Analysis - Evaluating potential issue with control group |  | Database | 2018-11-15 | 2018-12-07 | 2018-12-07 | We’re seeing indications that there MIGHT be a problem with the Ford program control group. Even when cut to a pretty granular level, Control is outperforming Treated for several major campaigns (Loyal, Declined Service, Defector—so both cadence and ad hoc). It’s possible that the program just doesn’t work, but before settling on that explanation we’d like to confirm there’s no issue with control group process or data. | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 5-Healthy
Ford |  | Project Completed | Retail | Large daily file catch-up batches to process due to Ford data issues | Further delays due to Anderson Ford data clean-up, additional large catch-up file not in original plan and NCOA processing. Current ETA to get back on schedule is 11/27 | Campaign | 2018-10-29 | 2018-11-09 | 2018-11-27 | Ford is sending 2 batches of daily files per day the week of 10/29. Ford was not assigning CKS IDs to new sales and service records over a period of time due to an upstream issue and they need to reprocess all records impacted. FACET will need to manually process batch loads during this timeframe. Due to high data volumes, we are expecting to fully catch-up by 11/12. Campaign schedules will be impacted and will need to be monitored closely to ensure opt compliance. | None | None | 1-Concerns Realized | 5-Healthy | 5-Healthy | 5-Healthy | 2-Major Concerns | 1-Concerns Realized
Ford |  | Project Completed | Retail | KBB analysis for Q1 logic changes |  | Campaign | 2018-11-13 | 2018-11-30 | 2018-11-30 | Working with analytics team to provide analysis and counts for Q1 KBB logic changes | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Ford |  | Project Completed | Retail | Automate Adobe Campaign QC Checks |  | Continuous Improvement | 2018-08-01 | 2018-11-30 | 2018-11-30 | Automate Adobe QC checks in the database prior to delivering mail files. | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | Retail | infiniti Monthly Sales Event Campaign Data |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-03 | Montly Product Email Data creation and transfer to Harmony | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | Monthly Data ETL |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-04 | Montly data extraction from NCI CVM to Epsilon file share | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | October Nissan and Infiniti Lease, Loan and Cash EM Campaign QA |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-09 | Monthly Cadence emails require QA and transfer to Harmony | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | October Nissan and Infiniti Lease, Loan and Cash DM Campaign QA |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-09 | Monthly Cadence emails require QA and transfer to Print Vendors (VISO and IG) | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC DM |  | Campaign | 2018-10-01 | 2018-10-12 | 2018-10-11 | November Campaign (Tires, Brakes, General Service, Batteries) Live DM Updates | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Non Responder (Tires, Brakes Only) ER Reporting file |  | Database | 2018-10-10 | 2018-10-12 | 2018-10-12 | Updated file for Enterprise Reporting for Non Responder (Tires and Brakes Only) | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Campaign Phase 2 Segmentation Database Update |  | Database | 2018-08-24 | 2018-10-12 | 2018-10-11 | Update to NCI Seasonal data to support groups A-D | Delivered | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Conversant file |  | Campaign | 2018-10-02 | 2018-10-15 | 2018-10-18 | 4 Updated file layouts for Conversant from Adobe | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Conversant file |  | Database | 2018-10-02 | 2018-10-15 | 2018-10-18 | 2 Updated file layouts for Conversant from Database | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Waterfall Report |  | Database | 2018-10-03 | 2018-10-15 | 2018-10-15 | Waterfall for all golden records before dealerization | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | NCI Email Address Data Dump |  | Database | 2018-10-24 | 2018-10-26 | 2018-10-26 | Complete data dump of all Canadian email addresses and customer info | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical Campaign DM Deployment |  | Database | 2018-10-11 | 2018-10-15 | 2018-10-15 | Manual count, waterfall and data file pull for National Mechanical DM records | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Leaf Winter Tire Campaign |  | Campaign | 2018-09-01 | 2018-10-15 | 2018-10-15 | Season Recapture Campaign, targeting current Nissan Leaf owners | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Campaign Phase 2 Segmentation Campaign Update |  | Campaign | 2018-09-19 | 2018-10-16 | 2018-10-16 | Update to NCI Seasonal campaign to groups A-D | Delivered | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy
NCI |  | Project Completed | Retail | October Welcome Email Data |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-16 | Bi -Monthly Welcome Emails target list creation and transfer to Harmony | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Buyer Contact ID Addition |  | Database | 2018-08-31 | 2018-10-26 | 2018-10-26 | Adding buyer contact id to the F&I table to support Owner Profile report | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | October Welcome DM Data |  | Campaign | 2018-10-01 | 2018-10-31 | 2018-10-18 | Bi -Monthly Welcome DMs target list creation and transfer to Print Vendors (VISO and IG) | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical Campaign EM Deployment |  | Database | 2018-10-11 | 2018-10-27 | 2018-10-26 | Manual count, waterfall and data file pull for National Mechanical EM records including rescrub | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Campaign Phase 2 Segmentation Billing File Update |  | Database | 2018-09-20 | 2018-10-25 | 2018-10-02 | Update to NCI Seasonal billing data to support groups A-D | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC EM |  | Campaign | 2018-10-01 | 2018-10-29 | 2018-10-26 | November Campaign (Tires, Brakes, General Service, Batteries) Live EM Updates | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Campaign Deployment |  | Database | 2018-10-01 | 2018-10-29 | 2018-10-29 | Monthly Wholesale campaign | Delivered | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Campaign Phase 2 Segmentation Enterprise Reporting Update |  | Database | 2018-09-19 | 2018-11-02 | 2018-10-30 | Update to NCI Seasonal ER data to support groups A-D | Delivered | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | Retail | Projected vs Actual tables |  | Database | 2018-10-22 | 2018-11-08 | 2018-11-08 | Addition of tables to support automation of projected vs actual report | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Defector MCC Addition |  | Database | 2018-10-09 | 2018-11-05 | 2018-10-25 | Addition of MCC segmentation to Nissan Defector campaign | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Retail Loyalty Non Captive Flag |  | Database | 2018-10-15 | 2018-11-05 | 2018-10-16 | Addition of non captive flag for retail loyalty | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC November Campaign (Tires, Brakes, General Service, Batteries) DM Follow Up |  | Database | 2018-10-26 | 2018-10-31 | 2018-10-30 | Additional DM follow up to EM sent on 10/26, we have pushed the timing to nth hour and have west chicago team applying suppressions to met this late request | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale DM File Layout Updates |  | Database | 2018-11-05 | 2018-11-07 | 2018-11-07 | Update to the whole sale file layout to accommodate new segmentation | None | Management Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC ER Report updates for new segmentation |  | Database | 2018-10-26 | 2018-11-12 | 2018-11-12 | Update to Enterpirse reports for new segmentation | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC Non Responder Enterprise Reporting file for Defectors |  | Database | 2018-11-05 | 2018-11-13 | 2018-11-02 | Updates to ER File for Non Responders to TCC Defector campaign | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC Billing updates |  | Database | 2018-11-07 | 2018-11-13 | 2018-11-12 | Update to billing reports for new segmentation | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Phase 2 |  | Database | 2018-10-01 | 2018-11-15 | 2018-11-07 | Whole sale phase 2 - Addition of segmentation to ongoing National Mechanical campaign | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Follow Up Emails |  | Campaign | 2018-10-24 | 2018-11-18 | 2018-11-16 | Addition of 2 follow up emails to the Q4 Seasonal campaign on 10/30 and 11/18 | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Email Address Data Cleansing | This was cancelled due to low volume. We ran through Webula but need minimum $1k but only have approx $450 | Database | 2018-10-10 | 2018-11-15 | 2018-11-15 | Webbula email address cleansing | Not Started | STS Delays (Hardware/Software) | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 3-Warning | 4-Early Warning
Nissan |  | Project Completed | AfterSales | TCC Campaign Deployment - Defector |  | Campaign | 2018-11-09 | 2018-11-16 | 2018-11-15 | Quarterly NCI Aftersales campaign | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | MDW Testing |  | Campaign | 2018-10-18 | 2018-11-30 | 2018-11-08 | Testing new Automated ETL process that extracts NCI CVM data and encrypts and SFTP's to Epsilon via CLEO protocol. We will be testing to ensure the data coming into Epsilon is reflective of the CVM DB. | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Welcome DM Campaign Development - November |  | Campaign | 2018-10-24 | 2018-11-02 | 2018-11-02 | Monthly Campaign Deployment | 5-Healthy | None | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Retail Loyalty MCC Addition |  | Campaign | 2018-11-05 | 2018-12-01 | 2018-11-26 | Addition of MCC segmentation to Nissan Retail Loyalty campaign tables | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Dedupe Logic Update |  | Database | 2018-11-13 | 2018-11-21 | 2018-11-16 | Impliment Dedupe logic on mart due to Agility issue |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Defector MCC Addition |  | Campaign | 2018-10-09 | 2018-12-05 | 2018-11-05 | Addition of MCC segmentation to Nissan Defector campaign | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | INF OCP EM Bonus Cash Code Rule Update |  | Campaign | 2018-11-29 | 2018-12-06 | 2018-12-06 | Update campaign code to move records to Regular files if no match to back to BCC |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Defector Campaign Development - November |  | Campaign | 2018-11-01 | 2018-11-09 | 2018-11-09 | Monthly Campaign Deployment | Resources Needed | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | January Campaign Database changes |  | Database | 2018-11-01 | 2018-12-10 | 2018-12-10 | Changes to NCI Aftersales Seasonal to start monthly, changes to groups, coupons, etc | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | Retail | Harmony primary key change |  | Campaign | 2018-09-01 | 2018-12-10 | 2018-12-10 | Update all campaigns to use email_address_id as primary key rather than customer contact id | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Defector Campaign Development - November |  | Campaign | 2018-11-01 | 2018-11-09 | 2018-11-09 | Monthly Campaign Deployment | Resources Needed | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan OCP Campaign Development - November |  | Campaign | 2018-11-01 | 2018-11-16 | 2018-11-15 | Monthly Campaign Deployment | Resources Needed | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti OCP Campaign Development - November |  | Campaign | 2018-11-01 | 2018-11-19 | 2018-11-19 | Monthly Campaign Deployment | Resources Needed | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Agility Update |  | Database | 2018-11-13 | 2018-11-21 | 2018-11-21 | Update to Agility process to latest version |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Welcome EM Campaign Development - November |  | Campaign | 2018-11-01 | 2018-11-30 | 2018-11-30 | Monthly Campaign Deployment | Resources Needed | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Non Responder DM and EM Dealer URL list |  | Campaign | 2018-10-26 | 2018-11-01 | 2018-10-31 | Non Responder DM and EM Dealer URL list | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Group C English list |  | Campaign | 2018-10-25 | 2018-10-31 | 2018-10-31 | Group C English list pulled for account team research | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Nissan Whole Sale Undeliverable Report |  | Database | 2018-10-17 | 2018-11-26 | 2018-11-24 | Report of undeliverable emails for Whole Sale |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Campaign Deployment |  | Database | 2018-11-01 | 2018-11-26 | 2018-11-26 | Monthly Wholesale campaign | On-Time | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Addition of Seeds |  | Campaign | 2018-12-05 | 2018-12-28 | 2018-12-28 | Addition of seed list to the NCI aftersales campaign | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | NNA Sales File Encryption |  | Database | 2018-12-01 | 2018-12-21 | 2018-12-21 | File Encryption for all DM files | Resources Needed | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Q4 Seasonal Campaign Deployment |  | Campaign | 2018-09-25 | 2018-11-16 | 2018-11-16 | Quarterly NCI Aftersales campaign | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Non Responder DM and EM Dealer URL list |  | Campaign | 2018-10-26 | 2018-10-31 | 2018-10-31 | Client request for list of all non responder URLs | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Group C English list |  | Campaign | 2018-10-29 | 2018-10-31 | 2018-10-31 | Client request for list of Group C English | Delivered | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale GCS Return on Investment Reports |  | Database | 2018-10-11 | 2018-11-27 | 2018-11-24 | Additional business rules for the GCS Return on Investment Reports | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC Tires, Brakes, GS, Batteries Follow Up EM segmentation |  | Database | 2018-11-29 | 2018-12-03 | 2018-12-03 | Update to segmentation for TCC follow up email in database | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Business Intelligence |  | Project In-Progress | Retail | GM IMRBO Portal - Single Sign on with San Diego CSSR Portal using Token Approach |  | BI (Reporting/Dashboard) | 2018-10-01 | 2018-12-01 |  | GM IMRBO Portal - Single Sign on with San Diego CSSR Portal using Token Approach | On-Time | None | 4-Early Warning | 4-Early Warning | 5-Healthy | 4-Early Warning | 4-Early Warning | 4-Early Warning
Business Intelligence |  | Project In-Progress | Retail | GM IMRBO Portal - Single Sign on with San Diego CSSR Portal using SAML approach |  | BI (Reporting/Dashboard) | 2019-01-01 | 2019-02-01 |  | GM IMRBO Portal - Single Sign on with San Diego CSSR Portal using SAML approach | On-Time | None | 4-Early Warning | 4-Early Warning | 5-Healthy | 4-Early Warning | 4-Early Warning | 4-Early Warning
Nissan |  | Project Completed | Retail | Nissan OCP Campaign Development - December |  | Campaign | 2018-11-29 | 2018-12-14 | 2018-12-01 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Welcome Campaign Development - December |  | Campaign | 2018-11-28 | 2018-12-04 | 2018-12-04 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | VPP to Maritz |  | Campaign | 2018-11-26 | 2018-12-06 | 2018-12-05 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Defector Campaign Development - December |  | Campaign | 2018-11-26 | 2018-12-10 | 2018-12-10 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Defector Campaign Development - December |  | Campaign | 2018-12-03 | 2018-12-10 | 2018-12-10 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti OCP Campaign Development - December |  | Campaign | 2018-12-03 | 2018-12-17 | 2018-12-17 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Addition of Retail Loyalty value engine input file including FRMS |  | Database | 2018-11-09 | 2018-11-12 | 2018-11-12 | Additional file needed for Retail Loyalty campaign - value engine input file |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC Tires, Brakes, GS, Batteries Follow Up EM file |  | Campaign | 2018-12-03 | 2018-12-05 | 2018-12-05 | Update to segmentation for TCC follow up email in campaign | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Dedupe Logic Update |  | Database | 2018-11-26 | 2018-12-08 | 2018-12-08 | Additional logic to dedupe what is not consolidated by Agility |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Agility |  | Database | 2018-12-04 | 2018-12-10 | 2018-12-10 | Agility Hard Key Match researched and determined not viable |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Control Group |  | Database | 2018-09-06 | 2018-12-11 | 2018-12-11 | Adding control group in January mailing so do not start in middle of creative cycle, will be quarterly and every other quarter so Jan-Mar then July-Sept | Not Started | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical Control Group |  | Database | 2018-12-03 | 2018-12-11 | 2018-12-11 | Whole Sale National Mechanical Control Group |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical Waterfall Report |  | Database | 2018-12-03 | 2018-12-11 | 2018-12-12 | Whole Sale National Mechanical Ongoing Waterfall Report | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2018-12-10 | 2018-12-12 | 2018-12-12 | Update to Dealer Counts Report |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Database | 2018-11-27 | 2018-11-28 | 2018-11-28 | Upload Demo Accounts in Dev/QA Portal |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | TCC |  | Database | 2018-11-27 | 2018-11-28 | 2018-11-28 | Upload Demo Accounts in Dev/QA Portal | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2018-11-27 | 2018-12-27 | 2018-12-26 | Campaign Deployment - January | Client Commitment | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Welcome Campaign Development - January |  | Campaign | 2018-12-28 | 2019-01-07 | 2019-01-07 | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Database | 2018-12-18 | 2019-01-05 | 2018-12-21 | Gaps in Portal Investigation and Fix |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2018-12-11 | 2018-12-12 | 2018-12-12 | Update to Waterfall Report to include Control group for EM/DM | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - Q4 Tires Report for Analytics |  | Database | 2018-12-14 | 2019-01-09 | 2018-12-28 | Seasonal - Q4 Tires Report for Analytics |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Campaign | 2018-12-01 | 2019-01-09 | 2019-01-09 | Seasonal - January Campaign Deployment DM | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale Undelivered Report |  | Database | 2018-12-12 | 2018-12-14 | 2018-12-14 | Update to Waterfall Report to include Control group for EM/DM | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | NCI Q4 Seasonal Waterloo Nissan total SRC report |  | Database | 2018-12-05 | 2018-12-07 | 2018-12-07 | NCI Q4 Seasonal Waterloo Nissan total SRC fall customers report |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2018-12-17 | 2018-12-20 | 2018-12-20 | Matchback from Apr - July 2018 | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale ROI Analysis |  | Database | 2018-12-17 | 2018-12-20 | 2018-12-20 | GCS Rounding Prices/ROI Analysis | Resources Needed | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | NNA Aftersales File Encryption |  | Database | 2018-12-01 | 2018-12-21 | 2018-12-21 | File Encryption for all DM files |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Addition of Seeds table |  | Database | 2018-12-05 | 2018-12-13 | 2018-12-13 | Addition of seed list to the NCI aftersales campaign | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | January Campaign changes |  | Campaign | 2018-11-01 | 2019-01-11 | 2019-01-11 | Changes to NCI Aftersales Seasonal to groups, coupons, etc - in home date confirmed to 1/29 | On-Time | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Database | 2019-01-11 | 2019-01-15 | 2019-01-15 | Split of Billing file by Channel | 5-Healthy | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - Q4 |  | Database | 2019-01-05 | 2019-01-16 | 2019-01-09 | Tires Report for Analytics |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale New Changes to Mart Logic |  | Database | 2018-12-16 | 2018-12-21 | 2018-12-08 | Whole Sale New Changes to Mart Logic | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project In-Progress | Retail | Nissan Retail Loyalty Campaign Development |  | Campaign | 2018-04-25 | 2019-01-21 |  | Creation of Nissan Retail Loyalty Campaign including the Follow up campaign in Adobe | On-Time | Resources Needed | 2-Major Concerns | 5-Healthy | 5-Healthy | 5-Healthy | 4-Early Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Campaign | 2018-12-01 | 2019-01-11 | 2019-01-11 | Seasonal - January Campaign Deployment DM - Conversant | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | NCI Aftersales File Encryption |  | Database | 2018-12-01 | 2018-12-21 | 2018-12-21 | File Encryption for all DM files | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2018-12-28 | 2019-01-14 | 2019-01-14 | Campaign Deployment - February | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan Defector Campaign Development - January | Deployed early due to client request | Campaign | 2019-01-07 | 2019-01-17 | 2019-01-15 | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC Phase 3 | This is dependent on portal resource availability, updated planned end date due to their availability | Database | 2018-10-18 | 2019-01-06 | 2019-01-06 | Updates to the coupon tables to accomdate TCC phase 3 coupon changes, date pushed to 12/4 due to change in scope for portal team, moved out again due to portal resource availability | Not Started | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC File Changes |  | Campaign | 2019-01-03 | 2019-01-10 | 2019-01-10 | Update to TCC File to accommodate 2 coupon prices by concatonating prices for both EM/DM | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Nissan Retail Loyalty |  | Campaign | 2018-12-03 | 2019-01-21 |  | Monthly Campaign Deployment | 5-Healthy | Resources Needed | 2-Major Concerns | 5-Healthy | 3-Warning | 5-Healthy | 3-Warning | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Database | 2019-01-04 | 2019-01-09 | 2019-01-09 | Pre Counts Vs New Available Count Report |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | Welcome Campaign Investigation |  | Database | 2019-01-04 | 2019-01-21 | 2019-01-24 | Steve found 4 additional issues on 1/7, Steve not able to complete all comparisons but will today 1/10, Sami pulled for Jan, Steve also pulled as parallel test and looked good but had some additional records that look correct, Steve will review with Sami as of 1/15 - Sami found in previous run - Steve is now rerunning on 1/17 |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Tires) March Additional Pre-Counts for 10 Dealers | Additional dealer was included and extended time needed | Database | 2019-01-16 | 2019-01-21 | 2019-01-28 | TCC - (Tires) March Additional Pre-Counts for 10 Dealers |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan OCP Campaign Development - January |  | Campaign | 2018-12-23 | 2019-01-16 | 2019-01-16 | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Defector Campaign Development - January |  | Campaign | 2019-01-07 | 2019-01-17 | 2019-01-17 | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February |  | Campaign | 2019-01-08 | 2019-01-14 | 2019-01-10 | Concatonate Price for EM | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti OCP Campaign Development - January |  | Campaign | 2018-12-21 | 2019-01-18 | 2019-01-18 | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February |  | Database | 2019-01-11 | 2019-01-17 | 2019-01-17 | Caps vs Non Caps Flag - Add to Database tables |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2019-01-04 | 2019-01-18 | 2019-01-18 | Pull Harmony Activity data for analytics reporting needs | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical Harmony Code Changes |  | Database | 2019-01-18 | 2019-01-23 | 2019-01-23 | Whole Sale Harmony Activity Code Changes |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February |  | Campaign | 2019-01-18 | 2019-01-22 | 2019-01-22 | Caps vs Non Caps Flag - Add to Campaign | Resources Needed | None | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Campaign | 2018-12-01 | 2019-01-21 | 2019-01-21 | Seasonal - January Campaign Deployment EM | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC |  | Database | 2018-12-13 | 2018-12-15 | 2018-12-15 | Add Price Attributes for coupons |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC |  | Database | 2018-12-30 | 2019-01-02 | 2019-01-02 | Model Count Report |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project In-Progress | AfterSales | Seasonal - January | Waiting to hear if cadence needs this | Database | 2019-01-11 | 2019-02-28 |  | File to compare with cadence for anomalies | 5-Healthy | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Tires) March Provide ENTP data dump |  | Database | 2019-01-17 | 2019-01-28 | 2019-01-28 | TCC - (Tires) March Provide ENTP data dump |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Repair Order data feed | This is dependent on client resource availability | Database | 2018-08-03 | 2019-01-25 | 2019-01-25 | New CVM feed for Repair Order data, Date moved from 11/30 to 1/25 due to client availability | On-Time | Client Commitment | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC |  | Database | 2019-01-04 | 2019-01-11 | 2019-01-11 | Pull Harmony Activity data for analytics reporting needs | None | Resources Needed | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Owner Profile Phase 2 |  | Database | 2018-10-17 | 2019-02-28 |  | More than 3 years of data in specific transactional tables and additional tables to support Owner Profile Phase 2 | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January |  | Campaign | 2018-12-01 | 2019-01-22 | 2019-01-22 | Seasonal - January Campaign Deployment EM - Conversant | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February |  | Campaign | 2019-01-04 | 2019-01-23 | 2019-01-23 | Monthly Campaign Deployment |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical | Waited for client approval | Database | 2018-12-28 | 2019-01-27 | 2019-01-31 | Campaign Deployment - February | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project In-Progress | AfterSales | Seasonal - January |  | Database | 2019-01-11 | 2019-02-08 |  | Additional Language Preference Column to 2 Dealer Imprint Tables | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | TCC Tires, Brakes, GS, Batteries Enterprise Reporting updates |  | Database | 2018-12-14 | 2019-02-08 |  | Update to segmentation for TCC Enterprise Reporting | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Not Started | AfterSales | Seasonal - January |  | Campaign | 2019-02-01 | 2019-02-15 |  | Seasonal - January Campaign Deployment EM Follow Up 1 | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Not Started | AfterSales | Whole Sale National Mechanical |  | Database | 2019-01-28 | 2019-02-18 |  | Campaign Deployment - March | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | AfterSales | Seasonal - January Portal Snapshot Inflated numbers |  | Campaign | 2019-01-03 | 2019-01-08 | 2019-01-09 | Seasonal - January Campaign Portal Snapshot Inflated numbers | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | Whole Sale National Mechanical |  | Database | 2019-01-07 | 2019-01-16 | 2019-01-16 | Split of the Mechanical and Collision segments |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC Harmony Activity Report |  | Database | 2019-01-04 | 2019-01-11 | 2019-01-11 | Provided data dump on 1/4 but need additional data on 1/11 |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February |  | Campaign | 2019-01-04 | 2019-01-11 | 2019-01-11 | Update to TCC - (Brakes, General Service) February to use Pre-Maritz data and pull DM and EM proof files |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February Caps vs Non Caps |  | Database | 2019-01-10 | 2019-01-14 | 2019-01-14 | Create tables and update scripts to allow non caps into campaign, billing, reporting with different rules |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | AfterSales | TCC - (Brakes, General Service) February Repair of EM file load process |  | Database | 2019-01-10 | 2019-01-15 | 2019-01-15 | TCC - (Brakes, General Service) February Repair of EM file load process |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | Whole Sale National Mechanical |  | Database | 2019-01-28 | 2019-02-18 |  | Campaign Deployment - March | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | Wholesale File Encryption |  | Database | 2018-12-01 | 2019-02-21 |  | File Encryption for all DM files |  | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | TCC Tires, Brakes, GS, Batteries billing updates |  | Database | 2018-11-28 | 2019-02-25 |  | Update to segmentation for TCC billing | Not Started | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | Whole Sale Adobe Instance |  | Campaign | 2018-09-20 | 2019-02-28 |  | Need separate Adobe instance for Whole Sale campaigns, Date moved from 11/30 to 12/30 due to hardward needed | On-Time | STS Delays (Hardware/Software) | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Not Started | AfterSales | Seasonal - January |  | Campaign | 2019-03-01 | 2019-03-08 |  | Seasonal - January Campaign Deployment EM Follow Up 2 | 5-Healthy | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | Whole Sale Prospect data |  | Database | 2019-01-18 | 2019-04-01 |  | Addition of Whole sale prospect data to Nissan MDW |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti OCP Incentive Exclusion |  | Campaign | 2019-01-08 | 2019-01-18 | 2019-01-18 | Additional incentive exclusions added to the Infiniti OCP campaign |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | NNA Aftersales Caps vs Non Caps Field change |  | Campaign | 2019-01-18 | 2019-01-22 | 2019-01-22 | Change Adobe campaign to use Total Available Count field |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | AfterSales | NNA Aftersales Caps vs Non Caps code addition |  | Database | 2019-01-08 | 2019-01-14 | 2019-01-14 | Database code change to accommodate non caps including addition of Total Available Count field | None | Resources Needed | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy
Nissan |  | Project Completed | Retail | Dms OptOut File |  | Database | 2019-01-21 | 2019-01-22 | 2019-01-22 | Addition of DMS Opt Out file |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | NCI New Scripts |  | Database | 2019-01-21 | 2019-01-25 | 2019-01-25 | New Scripts / Feeds from NCI to fix deleted/not merged records |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Retail | NCI Customer and Owner type table additions |  | Database | 2019-01-21 | 2019-01-25 | 2019-01-25 | Customer and Owner type table additions |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Infiniti Defector and Infiniti OCP DM Household Requirement |  | Database | 2019-01-21 | 2019-01-25 | 2019-01-25 | Infiniti Defector and Infiniti OCP DM Household Requirement |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project Completed | Retail | Nissan OCP Last 6 Months Counts Per Vehicle | Urgent client campaign reporting request | Campaign | 2019-01-02 | 2019-01-25 | 2019-01-25 | Nissan OCP Last 6 Months Counts Per Vehicle |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
NCI |  | Project Completed | Both | Missing Harmony Opt Data |  | Database | 2019-01-25 | 2019-01-29 | 2019-01-29 | Set up 2 feeds to intake INF and NIS opt feeds |  | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Infiniti Welcome Campaign Development - February |  | Campaign | 2019-02-01 | 2019-02-06 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Nissan Defector Campaign Development - February |  | Campaign | 2019-02-04 | 2019-02-11 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Nissan OCP Campaign Development - February |  | Campaign | 2019-02-05 | 2019-02-15 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Infiniti Defector Campaign Development - February |  | Campaign | 2019-02-04 | 2019-02-11 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Infiniti OCP Campaign Development - February |  | Campaign | 2019-02-05 | 2019-02-18 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | AfterSales | TCC - (Tires) March |  | Campaign | 2019-01-31 | 2019-04-22 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Infiniti Welcome Campaign Development - March |  | Campaign | 2019-03-01 | 2019-03-06 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Nissan Defector Campaign Development - March |  | Campaign | 2019-03-01 | 2019-03-11 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Nissan OCP Campaign Development - March |  | Campaign | 2019-03-04 | 2019-03-14 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Infiniti Defector Campaign Development - March |  | Campaign | 2019-03-01 | 2019-03-11 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Nissan |  | Project In-Progress | Retail | Infiniti OCP Campaign Development - March |  | Campaign | 2019-03-05 | 2019-03-18 |  | Monthly Campaign Deployment | None | None | 5-Healthy | 3-Warning | 5-Healthy | 5-Healthy | 5-Healthy | 5-Healthy
Note on C64: Author: We are really waiting on data for this right? Yes, waiting on Facebook data.

## Open_Status (hidden)
Project Completed
Project Delivered
Project Deployed
Project In-Progress
Project Late
Project Not Started
Project On-Hold
Project On-Time

## Project_Status (hidden)
Not Started
On-Time
Delivered
Late
On-Hold

## Scores (hidden)
1-Concerns Realized
2-Major Concerns
3-Warning
4-Early Warning
5-Healthy

## Client_Names (hidden)
Autonation
BMWFS
GM
AT&T
Nissan
NCI
Business Intelligence
Ford
GM Financial
BMWNA

## Project_Constraints (hidden)
Resources Needed
STS Delays (Hardware/Software)
Management Commitment
Client Commitment
Scope Creep
Budget
None